## V1.0
Week 01 | [6 empty] | Week 02 | [6 empty] | Week 03 | [6 empty] | Week 04 | [6 empty] | Week 05 | [6 empty] | Week 06 | [6 empty] | Week 07 | [6 empty] | Week 08 | [6 empty] | Week 09 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
 | time axis 2020-01-27 to 2020-05-10
Idea | [6 empty] | Requirements | [11 empty] | Design | [32 empty] | Implementation | [36 empty] | Portfolio
Task Formation and Idea Decision
Initial Planning
Idea G. Meeting
(LJ) Minute 01
(LJ) Mission Statement
(JC) Mission Objectives
(DP) System Boundary Diagram
(LS) User Views and Requirements
(BC) Transaction Requirements
(TB) System Requirements
(LJ) Planning / Gannt
Requirements G. Meeting
(LJ) Minute 02
(LJ) Global Logical Data Model
(DP) Data Dictionary
(TB) Logical Table Structure
(TB) Physical Table Structure
(JC/LS) Interface Design
(BC) Transaction Matrix
Design G. Meeting
(LJ) Minute 03
Planning G. Meeting
(LJ) Minute 04
Research For the Implementation and Refining Individual Design Work
Design G. Meeting
(LJ) Minute 05
Brainstorming G. Meeting
(LJ) Minute 06
Implementation Brainstorming
Meeting 07
(LJ) Minute 07
Design Review Meeting
(LJ) General Area - Online Integration
(DP) General Area - Android Version
(BC) General Area - Database Integration
(LS) - General Area - Desktop Version
(TB) - General Area - Database Design
(JC) General Area - User Interface